## Sheet1
Mitigated? | Date | Risk Type | Owner | Risk | Likelihood | Impact / Consequence | Risk Level | Action | Planning / Control
No | 2024-03-01 | Schedule | John Doe | Project timeline may be overly optimistic, leading to delays in deliverables. | 5 | 3 | 15 | Mitigate | This can be mitigated by utillising story point estimates and closely monitering the teams velocity so that it can be addressed early by descoping items in order of lowest priority
[5 empty] | 2 | 5 | 10
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Sheet4
Likeliness Definitions
1 - Rare:
2 - Unlikely:
3 - Possible:
4 - Likely:
5 - Almost certain:
Impact/Consequence Definitions
1 - Negligible:
2 - Minor:
3 - Moderate:
4 - Major:
5 - Catastrophic:
Risk Level Ratings
Extreme risk (20-25): | The process, task or activity in question must not occur or must cease until actions are taken to eliminate the hazard or minimise the risk. Team oversees specific review of effectiveness of new or additional controls before process, task or activity can commence or recommence
Very high risk (15-16): | Actions are to be taken to eliminate the hazard or minimise the risk.The Project Manager oversees action plans and receives reports on progress. Specific consideration of control effectiveness and new or additional control options to be considered
High risk (10-12): | Actions are to be taken to eliminate the hazard or minimise the risk. Project Manager oversees action plans and receives reports on progress. Periodic consideration of control effectiveness and new or additional control options to be considered
Moderate risk (4-9): | Relevant Project Manager oversees action plans and receives reports on progress. Periodic consideration of control effectiveness and new or additional control options to be considered (nzta.govt.nz, n.d.).Actions are to be taken to eliminate the hazard or minimise the risk.
Low risk (1-4): | The process or activity in question continues with existing controls. Ongoing monitoring of existing control effectiveness (within agreed business as usual (BAU) arrangements). Continue to reduce the risk by adopting any improvements in safety the business becomes aware of